# APL e-Card Project Plan

Revised: September 28, 2006

Project Name: APL e-Card

Project Description:  APL e-Card is designed to develop a department charge account to prepaid Airfare and Local Lodging expenses.

Project Start Date: February 2005

Project End Date:  September 2006 (phase 1)

Project Owner: Accounting and AdCom

## Project Schedule

| Task | Resource | Start Date | Target Date | Estimate | Status | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Analysis and Planning |
| Develop business analysis documents | Lorri | 11/1/05 | 01/31/06 |  | Done |  |
| Develop project plan | Jane | 12/13/05 | 02/28/06 |  | Done |  |
| Develop requirement document | Lorri Jane | 01/01/06 | 02/28/06 |  | Done |  |
| SDLC Review | Adcom Mgt. | 02/08/06 | 02/08/06 |  | Done |  |
| Review requirement documents and final sign off | Rich Diana Lorri | 02/21/06 | 02/28/06 |  | Done | Requirement sign off occurred on 3/1/06 |
| Develop business process flow chart | Lorri Jane |  | 12/31/05 | 80 hours | Done |  |
| Prototype of screen shots | Jyoti |  | 12/31/05 | 80 hours | Done |  |
| Use case analysis and modeling | Jane | 01/01/06 | 02/28/06 | 80 hours | Done |  |
| Risk Analysis and document | Lorri Bent | 03/10/06 | 06/15/06 | 80 hours | Done | Received on 9/19/06 |
| Design Review and Plan for implementation | Jane | 03/10/06 | 03/30/06 | 80 hours | Done |  |
| Coding and Testing |
| Developed work-breakdown schedule | Jane | 02/01/06 | 02/28/06 | 20 hours | Done |  |
| Develop and implement APL e-Card/SNAP e-Content | Lorri | 04/01/06 | 07/30/06 | 80 hours | Done | Completed in snaptest |
| PayQuest Development APL Advance form dev Trip # GUI changes PAL/EDI data transmission Database changes Coversheet, email & misc changes | Jane | 04/15/06 | 06/30/06 | 800 hours | Done |  |
| PAL development Setup TPO screen PAL/EDI data process Create interface for PayQuest to access APL e-Card EDI data | Fran | 04/01/06 | 04/30/06 | 50 hours | Done | PAL/TPO changes on hold due to old TPO’s cleanup. Per Diana, cleanup will be done by 6/30. |
| APL Card/Ledger interface development Create/Post APL ledger from PQ to FS system Generate U.S. Bank invoice and post GL records from PAL | Jane Dave V. | 07/01/06 | 09/30/06 | 100 hours | In Review | PAL/APL GL is under review. |
| EDI Bank Interface negotiation and documentation | Lorri Antja U.S. Bank | 07/10/06 | 10/30/06 | 320 hours | In Progress | No progress on Trip# sending (as of 7/11), waiting for EDI master map from U.S. Bank |
| Testing with U.S. bank interface Hotel Airfare | Lorri Antja Fran Jane | 04/15/06 | 10/30/06 | 80 hours | In Progress | Progressing slowly EDI testing appears bumpy, extended testing period for hotel/airfare to 7/30/06 Loss key resource for PAL/EDI process due to retirement After 2+ months experience of EDI trials and errors, we’ve discovered EDI rules have not yet defined. Thus, We’re experimenting the new process instead of testing it. |
| APL Card Application Development Submit application Update/Cancel application Routing approval Application report Admin functions (inquire, report, etc) | Jane | 05/15/06 | 09/30/06 | 500 hours | In Progress | Phase I was rolled out on 9/9/06. Routing Approval will be on held because of Kuali workflow engine usage. Update is on held due to PAL/TPO edit restrictions. |
| APL/SAMS interface development Develop API to retrieve APL reviewer resource by ucinetid Setup APL reviewer function in SAMS | Jane Valerie | 07/15/06 | 08/31/06 | 80 hours | Not Started | Will be held due to workflow process. |
| Application module functional testing | Jane Lorri | 08/01/06 | 08/30//06 | 40 hours | Done |  |
| Develop and implement e-Learning content and exam module | Diana | 05/01/06 | 06/30/06 | 320 hours | Not Started | Initially Accounting will provide Classroom training. |
| Enable APL/e-Learning module in TED | Manjeet | 07/01/06 | 07/15/06 | 40 hours | Not Started | On hold due to the class room training plan |
| Testing Schedule Load testing Integration testing Functional testing | Jennifer Jane | 08/01/06 | 08/30/06 | 80 hours | Done |  |
| Rollout (Phase I) |
| Manage APL e-Card interface with U.S. bank | Diana Cristin | 08/01/06 | 12/31/06 |  | In Progress | Manage ongoing maintenance activities with U.S. bank |
| Pilot schedule & usability testing | Jane Lorri | 08/15/06 | 09/30/06 | 80 hours | In Progress | Two APL accounts have been issued to ICS and Social Sciences dept. to pilot. |
| Production rollout schedule | Jane Lorri | 09/05/06 | 09/30/06 |  | Done | Pilot edition is released to production on 9/9/06. |