APL e-Card Work Break Down Tasks

Project Plan

Last Updated: 6/1/2007 2:42:00 PM by Jane Gao

| No | Description | Begin Date | Target Date | Resource | Status | Comment |
| --- | --- | --- | --- | --- | --- | --- |
|  | Current Tasks |  |  |  |  |  |
|  | Incorrect TPO number received in PAL | 07/19/07 | 07/19/07 | Jane | Completed | TPO was created after the card was issued to cardholder, thus, PAL could not find the correct TPO to pass. |
|  | Add date range search criteria on Admin APL Source Date Detail on In progress and Pending EDI searches. | 02/20/07 | 5/31/07 | Samuel | Completed | Rollout on 5/30 |
|  | To Automate EDI/PALPayQuest/Ledger process, create Universal Commands to run Unix jobs and put them in IBM scheduler. | 05/09/07 | 05/31/07 | Jane Julie Antja Dave V. | Completed |  |
|  | SnapTest/APL eContent goes live | 05/07/07 | 5/14/07 | Sonja Jane | Completed | Snap/APL went live on 5/14. |
|  | Send a copy of APL suspension email to aplecard email list. Other email sends from aplecard account instead of travel-accounting. | 02/20/07 | 03/16/07 | Jane | Completed | Rollout 2/22/07 |
|  | Hotel confirmation code is sent over with last 4 digits card number, and not being loaded into PQ. | 2/2/07 | 2/15/07 | Jane Melissa | Completed | Code fixed on 2/5. Melissa needs to check with hotel. |
|  | Trip# from EDI checking needs to re-viewed, it carries VALID status for next transaction record | 1/31/07 |  | Jane | On Hold | Need to look into more when receiving more APL entries with Trip# |
|  | Ledger Date needs to be later than expense date, use calendar month as ledger month date. | 1/23/07 | 7/31/07 | Jane | In Progress | Need to review after FY closing. |
|  | Fix the check-in/check-out dates to allow future dates | 01/08/09 | 01/09/07 | Jane | Completed | Fixed on 1/9/07 |
|  | Add ApproverInfo into APL form | 12/15/06 | 01/15/07 | Jane | Completed | Rollout on 1/10/07 |
|  | Approver screen changes: . change the TPO to 8 digits instead of 9 digits. For example, T00001660. . Make Notes field optional for Approval, but required for rejected account. | 12/4/06 | 12/05/06 | Samuel | Completed |  |
|  | Review the existing account/fund line mapping to single FS dept. which cause problem for acct/fund belongs to multi departments. | 11/2/06 | 12/20/06 | Samuel | Completed | Rollout on 12/6/06 |
|  | Fix the exception error Cristin/Lorri encountered | 09/08/06 | 09/09/06 | Samuel | Done |  |
|  | Fix the double line notes problem | 09/08/06 | 09/29/06 | Samuel | Done |  |
|  | Add Decline feature in Admin. And Cancel feature on list screen | 09/08/06 | 09/09/06 | Samuel | Done | Rollout 11/1/06 |
|  | Add Approval/Decline and Cancel email sending features | 09/08/06 | 09/29/06 | Samuel | Done | Rollout 11/1/06 |
|  | Add transaction inquiry to track both in progress and paid EDI transactions by Source Date | 09/08/06 | 10/6/06 | Samuel | Done | Rollout 11/1/06 |
|  | Provided additional action icon (note) to allow both users and admin. To add supplemental notes, and append to existing notes with input timestamps | 09/08/06 | 09/09/06 | Samuel | Done |  |
|  | Disable back button on approve screen After approve, click back button errors | 09/11/06 | 09/15/06 | Samuel | On Hold |  |
|  | Manually change the 2 pilot department application sub code to 05 (was 03) | 09/11/06 | 09/15/06 | Jane | Done |  |
|  | Add 05 to the sub code list instead of hard coded with 03 | 09/18/06 | 09/22/06 | Samuel | Done |  |
|  | APL e-Card application rollout (8/26) | 08/26/06 | 8/26/06 | Jane | Done | Rollout 8/26 |
|  | Only allow originator to submit the application. Department user is able to view the WIP records. | 08/17/06 | 08/23/06 | Samuel | Done |  |
|  | Complete Web Security Test | 08/17/06 | 08/23/06 | Josh | Done |  |
|  | Complete Security Pre-Assessment List | 8/17/06 | 08/23/06 | Jane | Done |  |
|  | Add trash (delete) function to WIP records | 8/17/06 | 08/23/06 | Samuel | Done |  |
|  | Expand the phone number fields | 8/17/06 | 08/23/06 | Samuel | Done |  |
|  | Use department name as Admin’s dept dropdown list. | 8/17/06 | 08/23/06 | Samuel | Done |  |
|  | Allow user to choose department for multiple application entries |  |  |  | Pending Discussion |  |
|  | Review Update Rules, what can be updated, how to submit update |  |  | Lorri Jane | In Planning |  |
|  | Load All source code developed by Justin into subversion | 08/02/06 | 08/04/06 | Samuel | Done |  |
|  | Fix the secondary PQ validation error | 08/02/06 | 08/04/06 | Samuel | Done |  |
|  | Admin Page Display dept. Code in front of TPO number, along with numeric digit validation Add Decline icon at the main page | 08/07/06 | 08/11/06 | Samuel | In Planning |  |
|  | Add invalid acct/fund link on app. Form |  |  |  | In Planning |  |
|  | Form submission Load Testing | 08/02/06 | 08/15/06 | Jennifer Samuel | In Progress |  |
|  | Overview APL e-Card architecture with EA team | 03/01/06 | 03/15/06 | Jane EA team | Done | 3/10/06 workflow API needs to be discussed later |
|  | Implementation design Refine PAL interface layout Refine/decide FS ledger layout with accounting Database modeling Layout class diagram structure for application. Review SAMS interface (FS reviewer role setup) | 03/01/06 | 03/31/06 | Jane | Done |  |
|  | Modify Database to store APL EDI and ledger transaction data Map APL advance form to existing travel advance form Create new table pal_edi_info Map bank edi elements to table columns Create new table pq_ledger_info and pq_ledger_hist Map ledger posting fields to Apl advance elements | 03/01/06 | 03/31/06 | Jane | Done | New tables are created on thea payquest db only. Ledger month end control table will be done thru DWH API. |
|  | Add new advance sub type “APL e-Card” | 03/15/06 | 03/31/06 | Jane | Done | New advance sub code “APL” is created. |
|  | Setup TPO screen | 04/01/06 | 04/15/06 | Fran | Done |  |
|  | Generate EDI Test data file for PayQuest to store | 04/01/06 | 04/15/06 | Fran | Done |  |
|  | Develop a batch job to retrieve EDI/PAL data a. download edi data file from APL to payquest/ftp/inbox b.create new APLEdiWorker.java to read PAL/EDI data and header file c.store EDI data in table pal_edi_info Leave edi status as blank, | 04/04/06 | 04/30/06 | Jyoti | Done |  |
|  | U.S. bank EDI/PAL development | 04/15/06 | 05/30/06 | Fran Antja | In Progress | Progressing slowly due to the bumpy testing with U.S. bank. |
|  | U.S. Bank Interface Test Setup in TPO in PAL Apply U.S. Bank Account Charge Hotel expenses Credit Hotel expenses Charge Airfare Credit Airfare Load EDI data in PAL/Payquest Create APL form in payquest | 04/15/06 | 07/31/06 | Lorri Jane Antja Dave V. | In Progress |  |
|  | Develop a batch job to create APL advance form | 04/03/06 | 06/30/06 | Jane | Done | Reference requirements for Advance form edit rules. |
|  | Modify trip# changes to incorporate with APL e-Card rules - add “Requestor” once APL e-Card is selected. | 05/24/06 | 05/31/06 | Jane | Done |  |
|  | Modify PQ form to incorporate form ownership for APL AD form | 05/24/06 | 05/31/06 | Jane | Done |  |
|  | Modify directory, coversheet changes | 06/15/06 | 06/30/06 | Jane | Done |  |
|  | Modify report to disallow the paid link to check data for PAL and YCAL payment | 06/15/06 | 06/30/06 | Jane | Done |  |
|  | Develop admin functions for PayQuest operations to monitor the EDI transaction completion | 07/20/06 | 07/2006 | Jane | Pending |  |
|  | Develop email process to send email when Apl from is created in payquest and save the email in PQ db. | 06/01/01 | 06/30/06 | Jane | Done | Needs new wording. |
|  | Develop batch job to post APL/EDI data to ledger | 07/01/06 | 07/30/06 | Jane | In Planning |  |
|  | PayQuest function testing | 08/2006 | 08/2006 | Jane |  |  |
|  | PayQuest Load testing | 09/2006 | 09/2006 | QA team |  |  |
|  | Setup Subversion in eclipse | 06/01/06 | 06/30/06 | Jane | Done | Code loaded in eclipse |
|  | Application Development |  |  |  |  |  |
|  | Analysis & Design, Create new tables to store the application data Create new database APL class diagram | 03/01/06 | 03/31/06 | Jane | Done |  |
|  | Create application Develop application GUI prototype Build in business rules for submission | 07/17/06 | 07/31/06 | Justin | Done Under Review |  |
|  | Workflow Implementation Design application workflow template Implement APL routing with Adcom workflow API Role & Resource re-assign Notification sending | 06/15/06 | 06/30/06 |  |  | On held to build under Kuali’s workflow engine |
|  | View and reports development Application directory page (main page) History search function | 07/17/06 | 07/31/06 | Justin | Done Under Review |  |
|  | Update/Cancel application | 06/10/06 | 06/30/06 |  | Partially Done | Update is done, Cancel is not provided |
|  | SAMS interface Retrieve APL departmental reviewer | 06/2006 | 06/2006 |  |  | On Held |
|  | Application workflow testing | 06/2006 | 06/2006 | Jane |  | On Held |
|  | Develop SNAP/APL eContent page | 05/2006 | 06/2006 | Lorri |  |  |
|  | Develop eLearning and online exam program in TED | 05/2006 | 08/2006 | Lorri |  | Use in classroom training |
|  | Pilot Planning | 08/01/06 | 08/15/06 | Jane |  |  |
|  | Rollout planning | 09/2006 | 09/2006 | Jane |  | Tentative |